## Team
Week 0
Lightning Talk:
Lightning Talk
Week 1
Architectural Review:
Architechtural Review
Week 2
Microarchitectural Review:
Microarchitechtural Review

## Tyler
Week 0
Introduction Slide
Milestones & Evaluation
Team Responsibilities
Week 1
Algorithms to Accelerate - DTW
Verification of Original Plan
Week 2
Modular-Level Implementation

## Paridhi
Week 0
We spent this week deciding our project. Our first idea was a Roomba (automated vaccuum and mop) so I spent this week reading about SLAM before deciding that it is out of the scope of this project for now. Then when we thought about doing Just Dance I read a little about the different ways we would track the dancer (imu vs camera) and how much memory we would need.
Week 1
After we decided that we want to make Just Dance for our project, I read about the different ways to track body movements, image processing algorithms for detecting a body or parts of a body, and algorithms for comparing two videos. At the end of this week we had finalised that we wanted to do DTW for the comparision algorithm.
Week 2
I read about how DTW works, and the different ways to make it faster, and smaller so that it can fit on an FPGA and work in real time. Decided on an implementation we liked.
Week 3
Implemented and tested a basic DTW and custom shidt register. Will need to experiment with types of ditance and minimum units.

## Diego
Week 0
Week 1
Week 2

## Shantanu
Week 0
Week 1
Week 2