## Team
Week 0
Lightning Talk
Week 1
Architectural Review
Week 2
Microarchitectural Review
Week 3
Basic Building Blocks Implementation
Week 4
Processor/Accelerator Implementation
Week 5
Integrating individual modules & testing

## Tyler
Week 0 - Lightning Talk
Introduction Slide
Milestones & Evaluation
Team Responsibilities
Week 1 - Architectural Review
Algorithms to Accelerate - DTW
Verification of Original Plan
Week 2 - Microarchitectural Review
Modular-Level Implementation
Week 3 - Basic Building Blocks Implementation
cordic.sv, LUT.sv, counter.sv, cordic_iteration.sv, CORDIC_tb.sv
Week 4 - Processor/Accelerator Implementation
hier.sv, hier_tb.sv (incomplete)
angle_label_unit, angle_label_unit.sv
Week 5
hier.sv, hier_tb.sv
Continuing to write tests for the hierarchy

## Paridhi
Week 0
We spent this week deciding our project. Our first idea was a Roomba (automated vaccuum and mop) so I spent this week reading about SLAM before deciding that it is out of the scope of this project for now. Then when we thought about doing Just Dance I read a little about the different ways we would track the dancer (imu vs camera) and how much memory we would need.
Week 1
After we decided that we want to make Just Dance for our project, I read about the different ways to track body movements, image processing algorithms for detecting a body or parts of a body, and algorithms for comparing two videos. At the end of this week we had finalised that we wanted to do DTW for the comparision algorithm.
Week 2
I read about how DTW works, and the different ways to make it faster, and smaller so that it can fit on an FPGA and work in real time. Decided on an implementation we liked.
Week 3
Implemented and tested a basic DTW and custom shift register. Will need to experiment with types of ditance and minimum units.
Weeks 4 and 5
While testing DTW further, I realised that the basic version was missing half the functionality. Rewrote a more robust DTW and tested it. The score is much more accurate now.
Started working on the game loop.

## Diego
Week 0
Week 1
Week 2

## Shantanu
Week 0
Researched HPS on the DE1-SoC.
Tried to understand best way to get USB data onto board processes
Week 1
Decided that it would be easiest to interface with USB via drivers already in linux
Began researching linux image onto DE1-SoC - was stalled due to missing wiring (UART - USB)
Week 2
Tested out and understood the components of the FPGA-HPS Demo program
Began understanding how to work with USB through linux
Started working on software (c code) to push an image (bitmap) from the usb into the FPGA SDRAM
Week 3 - Basic Building Blocks Implementation
Debugged code to push an image onto SDRAM of FPGA - got it work.
Confirmed that software to push image worked via another software to get the image from FPGA SDRAM and place into USB.
Celebrated very briefly till I looked at the size of 1 bitmap and calculated what the size would be for the entire songs worth of bitmap.
Began investigating compression methods that can be applied ahead of time and then decompressed on the board - RLE encoding, using MJPEG, hard coding in the values
Week 4 - Processor/Accelerator Implementation
Did math on potential decompression techniques and made the realization that despite decompression - we would still be over our space limit (we are trying to avoid streaming)
Began experimenting with streaming solutions - a double buffer method. Created software to push each image into 2 dedicated addresses in the SDRAM. Software piece was working. Hardware was not.
Given timing constraints with Capstone deadline - made the decision that video due to space constraints and streaming complexity, will be hardcoded in for reference angles.
Shifted focus on Audio - began researching the Wolfson Codec and interfacing it with the SPI and SDRAM. Also researched different audio file types.
Week 5
While working through audio module - realized that there might be an uneccesary complexity between synchronizing our audio and video (video plan was to play through PC)
Began implementing a way for the video (including the audio) to be stored on my PC, but the play is triggered by the board. Successfully created software to communicate via COM port.
Week 6
Began the functionality of the video trigger from board. While trying to run it along side minilab 2 code, ran into an issue of FPGA being re-wired by JTAG.
Started looking through QSF file and learning more about how the board's programming impacts the hardware components.